## Slide 1
Work Package 1: [Preparation] |  |  |  |  |  |  |  |  |  | 
Duration: |  | M | 1 - M | 7 | Lead Beneficiary: Universidad de Salamanca and Universidad de San Carlos |  | USal (Coord) USAC (Deputy) |  |  | 
Objectives |  |  |  |  |  |  |  |  |  | 
Preparar la base para el proyecto de física EL-BONGO mediante el establecimiento de comunidades de investigación funcionales, Desarrollar un plan de estudios educativo integral y adaptado para cada RLC, Mejorar la colaboración internacional y las habilidades de gestión de proyectos del consorcio. |  |  |  |  |  |  |  |  |  | 
Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  | 
Task No | Nombre |  |  |  |  | Descripción |  | Participantes |  | Status
T1.1 | Construyendo Comunidades RLC |  |  |  |  | Articular el propósito y los objetivos de investigación de cada comunidad, asegurando un enfoque centrado y orientado a metas para las iniciativas científicas. Establecer el marco de gobernanza para gestionar las actividades y los recursos de la comunidad de manera efectiva, asegurando operaciones fluidas y una administración responsable. Establecer políticas y directrices que defiendan la conducta ética, faciliten el intercambio de datos y promuevan la inclusión y la equidad de género en nuestro trabajo colaborativo. Planificación de seminarios, talleres y hackatones anuales. |  | UPCité, UCV, USAC and community members |  | Diciembre 2024 a Agosto de 2025 OK https://elbongo.redclara.net/wp-content/uploads/2025/07/Report_on_RLC_Communities_30052025.pdf
T1.2 | Plan de Estudios (Syllabus) de la Comunidad y Vida Académica |  |  |  |  | Definir el programa de capacitación de la comunidad adaptando el plan de estudios del modelo LA-CoNGA. |  | USal, USFQ, UNAH and community members |  | Diciembre 2024 a Agosto de 2025 En proceso
T1.3 | Comunidad ORI |  |  |  |  | Identificar las habilidades, perfiles y actividades de las ORI en el consorcio de socios. |  | UT3, UAN, USFQ, RedCLARA UCV, USB, UIS, ESPOCH, UNMSM, USAC, UFG, , UES, UNAH |  | Diciembre 2024 a Agosto de 2025 OK https://elbongo.redclara.net/wp-content/uploads/2025/07/Report_on_RLC_Communities_30052025.pdf
T1.4 | Programa de capacitación |  |  |  |  | Establecer el programa de capacitación de las ORI (contenido, metodología y responsables de la formación). |  | UT3, UAN, USFQ, RedCLARA UCV, USB, UIS, ESPOCH, UNMSM, USAC, UFG, UES, UNAH |  | Diciembre 2024 a Agosto de 2025 Programado para 2026
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
Work Package 1
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 2
MS1.1 | Researchers trained in MiLAB | 1 | UIS | Researches of all RLC (including IRO) trained in MiLAB facilities |  | M4 | Number of reseachers/teachers trainned
MS1.2 | RLC website | 1 | USAC | All RLC website available with all information about the community |  | M6 | Access to each website
Deliverable No | Deliverable Name | Work Package No | Lead Beneficiary | Type | Dissemination Level | Due Date (month number) | Description (including format and language)
D1.1 | Report on RLC | 1 | USal | R | SEN | M6 | A report describing how to implement and operate each RLC: Members, responsible parties, research topics, equipment needed, and training program. It will also include the IRO particular case. Format: electronic doc in a repository. 60-80pg Language: English
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024
Milestones and deliverables (outputs/outcomes) |  |  |  |  |  | 
Milestone No | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month n°) | Means of Verification

## Slide 3
Work Package 2: Development |  |  |  |  |  |  |  |  |  | 
Duration: |  | M | 5 - M24 | Lead Beneficiary: Universidad Nacional Mayor de San Marcos. Deputy Universidad Industrial de Santander |  |  | UNMSM (Coord), UIS (Deputy) |  |  | 
Objectives |  |  |  |  |  |  |  |  |  | 
Desarrollar una Red FABLab: Determinar las necesidades de equipamiento de la comunidad. Coordinar la adquisición e instalación de cada FABLab. Construir el ecosistema RLC fomentando sinergias y colaboración entre las comunidades, organizando actividades intercomunitarias y capacitando a los profesores. Desarrollar un Science Gateway para recopilar y difundir todos los contenidos producidos por el ecosistema RLC. Creando un espacio dentro del ecosistema RLC. |  |  |  |  |  |  |  |  |  | 
Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  | 
Task No | Nombre |  |  |  | Descripción |  |  | Participantes |  | Status
T2.1 | FABLab Setup |  |  |  | Determine the required physical infrastructure for each RLC: 3D printers, laser cutters, CNC, and various electronic supplies/tools. Compiling a list of requirements for installing the determined equipment at each partner Univ. |  |  | UNMSM, UAN, UPCite, USAC, UFG and ESPOCH |  | Marzo a noviembre de 2025 OK
T2.2 | Integration of Instrumentation Course |  |  |  | Adaptar el curso de instrumentación para cada RLC, incorporando el aprendizaje basado en proyectos para la colaboración y desarrollando módulos que combinen teoría y práctica en la fabricación digital para una adquisición equilibrada de habilidades |  |  | UNMSM, UAN, UPCite, USAC, UFG and ESPOCH |  | Marzo a noviembre de 2025 En proceso
T2.3 | Online Workshops and Training Sessions |  |  |  | Desarrollar talleres en línea con todos los FABLabs asociados (formación de formadores), abarcando desde la operación de maquinaria hasta técnicas avanzadas, con el apoyo de recursos en línea. |  |  | UNMSM, UAN, UPCite, USAC, UFG, and ESPOCH |  | Marzo a noviembre de 2025 En proceso
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
Work Package 2
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 4
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
T2.4 | Red de FABLab Operacional | La red FABLab estará completamente operativa, con dos centros (hubs) para la creación de prototipos y pruebas. La herramienta G-LAB comparte actualizaciones de diseño. | UNMSM, UAN, UPCite, USAC, UFG, ESPOCH | Enero de 2026 a noviembre de 2027
T2.5 | Actividades Intercomunitarias: Sinergia y oportunidades de colaboración | A través de mesas redondas, sesiones de lluvia de ideas y grupos focales con todos los RLC, buscar áreas potenciales de sinergia y colaboración, especialmente en el aprovechamiento de la IA y las herramientas computacionales. Este enfoque de capacitación compartida garantiza que, si bien cada comunidad conserva su singularidad, existan áreas comunes de aprendizaje que beneficien a todos los miembros. Implementar actividades intercomunitarias como talleres, seminarios, hackatones e iniciativas de ciencia ciudadana. | USFQ, USAC, UES, UNAH, USAL, UPCite | Junio a noviembre de 2025 En proceso – Dennis, Rodrigo, Mario Ruiz, Lucio Villanueva, Camilo, José Ocariz
T2.6 | Requisitos, planificación y diseño de la pasarela científica (Science Gateway) | Realizar entrevistas con los miembros de la comunidad. Documentar los requisitos funcionales y no funcionales, los roles de usuario, los tipos de contenido, las características de interacción y las medidas de seguridad. Definir la arquitectura de la Pasarela Científica, asegurando la escalabilidad, el rendimiento y la integración con MiLAB. Utilizar la interfaz de Diseño UI/UX para adaptarla a las diversas necesidades de los diferentes miembros de la comunidad. | UIS, INSA, UFG, CEDIS, RedCLARA, CIEMAT | Septiembre a noviembre de 2025 * Falta documentación oficial para cargar en la página web
T2.7 | Proceso de desarrollo, pruebas, y garantía de calidad del Science Gateway | Implementar un proceso de desarrollo ágil con sprints iterativos y retroalimentación periódica. Crear un espacio de colaboración MiLAB en el ecosistema RLC, integrando G-lab, CompLab y DataLab. Desarrollar ChatLAB y APIs para la integración de servicios de la comunidad de física EL-BONGO. Realizar pruebas exhaustivas de los puntos de integración de la aplicación. Llevar a cabo la aceptación de usuario de las pruebas alfa y beta con usuarios reales para garantizar la funcionalidad, usabilidad y confiabilidad del portal. | UIS, INSA, UFG, CEDIS, RedCLARA, CIEMAT | Enero a diciembre de 2026
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 5
Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  | 
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description |  | Due Date (month number) |  |  | Means of Verification
MS2.1 | Purchase orders | 2 | UAN | Purchase orders the FABLab equipment and supplies |  | M4 |  |  | Mail sent to the equipment providers
MS2.2 | FABLab Installation | 2 | UNMSM | All FABLab equipment Installed |  | M12 |  |  | Pictures of the equipment, videos of its operation
MS2.3 | Science Gateway Beta testing release | 2 | UIS | Beta Release the Science Gateway for partner testing. include performance evaluations, user feedback sessions, and iterative improvements based on the outcomes of these tests. |  | M20 |  |  | Web access to the Science Gateway
MS2.4 | The official launch of the Science Gateway | 2 | UIS | Involves training sessions, workshops, or webinars to familiarise users with the gateway's functionalities and encourage its adoption |  | M24 |  |  | Survey opinion among the partners
Deliverable No | Deliverable Name | Work Package | Lead Beneficiary | Type | Dissemination Level |  | Due Date | Description | 
D2.1 | FABLabs from A to Z | 2 | UNMSM | R | SEN |  | M20 | Especifying the needs for a FABLab installation. Requirements of space, ventilation, power, furniture, space, safety, storage for chemicals and reagents, and data communication infrastructure. The installation and operation of the equipment and network operation Format: electronic doc in a repository. 80-100pg Language: English | 
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 6
WP2 Estimated budget — Resources (n/a for prefixed Lump Sum Grants) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Participan t | Costs |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A. Personnel [Pers/month ¦Eur] |  | B. Subcontrac | C.1a Travel |  |  | C.1b Accomod | C.1c Subsisten | C.2 Equipment | C.3 Goods and services | D.1 Support to third parties |  | E. Indirect costs | Total costs
UPCité | 1 | 5600 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 5600.0
UT3 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0
INSA | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
D2.2 | EL-BONGO physics Science Gateway | 2 | UIS | R | SEN | M24 | Detailed report including requirements specification, Project Plan and Design Specifications; Documentation, API and Integration; Compliance and Security; Guidelines, Content Curation; Testing and Quality Assurance Plans; Training Materials; Maintenance. Format: electronic doc in a repository. 80-100pg Language: English
D2.3 | Repository for datasets, experimental workflows, and computational tools | 2 | UNMSM | DATA | SEN | M24 | Establish an open-access digital repository for datasets, experimental workflows, and computational tools used within EL-BONGO.
D2.4 | Report on VRLC engagement across the network for FabLab tools & skilss | 2 | USAL | R | SEN | M24 | Report on VRLC engagement across the network of partner institutions using digital FabLab tools & skills in Science
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 7
USal | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0
UIS | 3 | 5360 | 18144 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 17268.0 | 0.0 | 0.0 | 0.0 | 0.0 | 40772.0
UAN | 6 | 11840 | 19602 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 11693.7 | 0.0 | 0.0 | 0.0 | 0.0 | 43135.7
UNAB | 1 | 1600 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 1600.0
USFQ | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 15290.3 | 0.0 | 0.0 | 0.0 | 0.0 | 15290.3
EsPoCh | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 22186.7 | 0.0 | 0.0 | 0.0 | 0.0 | 22186.7
UES | 1 | 2160 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 25261.3 | 0.0 | 0.0 | 0.0 | 0.0 | 27421.3
UFG | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 25261.3 | 0.0 | 0.0 | 0.0 | 0.0 | 25261.3
USAC | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 25261.3 | 0.0 | 0.0 | 0.0 | 0.0 | 25261.3
UNAH | 0 | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 25261.3 | 0.0 | 0.0 | 0.0 | 0.0 | 25261.3
UNMSM | 2 | 3760 | 15876 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 18528.1 | 0.0 | 0.0 | 0.0 | 0.0 | 38164.1
UCV | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 14991.0 | 0.0 | 0.0 | 0.0 | 0.0 | 14991.0
USB | 0 | 0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 14991.0 | 0.0 | 0.0 | 0.0 | 0.0 | 14991.0
Total | 14 | 30320 | 53622.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 215994.0 | 0.0 | 0.0 | 0.0 | 0.0 | 299936.0
Work Package 3: Training and Education |  |  |  |  |  |  |  |  |  |  |  | 
Duration: |  | M | 13 | - M36 | Lead Beneficiary: Universidad Central de Venezuela and Universidad Nacional Autónoma de Honduras |  |  | UCV (Coord) UNAH (Deputy) |  |  |  | 
Objectives |  |  |  |  |  |  |  |  |  |  |  | 
Implement two student cohorts for each community. Schedule the corresponding modules for the training community courses (disciplinary and transversal) Develop internship plans and organise various academic activities, including seminars, workshops, conferences, hackathons and International schools. |  |  |  |  |  |  |  |  |  |  |  | 
Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  | 
Task No | Task Name |  |  |  |  | Description |  |  | Participants |  |  | Subcontracting
 |  |  |  |  |  |  |  |  | Name |  | Role | 
T3.1 | Cohort-Based Learning Structure |  |  |  |  | Schedule the corresponding modules for the training community courses (disciplinary and |  |  | UCV, UNAH, UIS UAN, USAC, UFG, UT3, |  | BEN | No
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
Work Package 3
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 8
 |  |  |  | transversal). Establish continuous feedback mechanisms to track student progress. |  |  | UPCite, USal, INSA, UNAB, USFQ, UNMSM |  |  |  |  |  |  | 
T3.2 | Internship Program |  |  | Develop internship plans to promote student mobility. Manage and monitor the internship programs, ensuring they provide meaningful learning experiences. |  |  | UCV, UNAH, UIS UAN, USAC, UFG, UT3, UPCite, USal, INSA, UNAB, USFQ, UNMSM |  |  |  | BEN | No |  | 
T3.3 | Virtual International School: |  |  | Organise a one-week virtual network school after each student cohort to provide additional learning opportunities, foster community engagement, and benefit the broader community ecosystem. |  |  | UCV, UNAH, UIS UAN, USAC, UFG, UT3, UPCite, USal, INSA, UNAB, USFQ, UNMSM |  |  |  | BEN | No |  | 
T3.4 | Academic Extracurricular Activities: |  |  | Plan and execute various academic activities such as seminars, workshops, conferences, and hackathons. Incorporate citizen science activities to engage students with social responsibility. |  |  | UCV, UNAH, UIS UAN, USAC, UFG, UT3, UPCite, USal, INSA, UNAB, USFQ, UNMSM |  |  |  | BEN | No |  | 
Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Milestone No (continuous numbering not linked to WP) |  | Milestone Name | Work Package No |  | Lead Beneficiary | Description |  |  | Due Date (month number) |  |  |  |  | Means of Verification
MS3.1 |  | Launching First Cohort Community training program | 3 |  | UCV and UNAH | Presentation of the program courses' contents and staff in charge to the students. |  |  | M12 |  |  |  |  | Video recording of the event
MS3.2 |  | Launching Second Cohort Community training program | 3 |  | UCV and UNAH | Presentation of the program courses' contents and staff in charge to the students. |  |  | M24 |  |  |  |  | Video recording of the event
Deliverable No |  | Deliverable Name | Work Package |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  |  | Description (including format and language) | 
D3.1 |  | Ecosystem training program report | 3 |  | UCV and UNAH | R |  | SEN |  | M36 |  |  | Report describing the two-year operation of the academic program. Include impact statistics from surveys. Format: electronic doc in a | 
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 9
WP3 Estimated budget — Resources (n/a for prefixed Lump Sum Grants) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Participan t | Costs |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A. Personnel [Pers/month ¦Eur] |  | B. Subcontrac | C.1a Travel |  |  | C.1b Accomod | C.1c Subsisten | C.2 Equipment | C.3 Goods and services | D.1 Support to third parties |  | E. Indirect costs | Total costs
UPCité | 4 | 18440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18440
UT3 | 2 | 8560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8560
INSA | 2 | 8560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8560
USal | 3 | 14160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14160
UIS | 4 | 6960 | 0 | 6 | 6 | 2574 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 18534
UAN | 7 | 13440 | 0 | 4 | 4 | 1716 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 21156
UNAB | 3 | 4800 | 0 | 4 | 4 | 1716 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 12516
USFQ | 3 | 4800 | 0 | 4 | 4 | 1716 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 12516
EsPoCh | 3 | 4800 | 0 | 6 | 6 | 2574 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 16374
UES | 3 | 4800 | 0 | 6 | 6 | 2574 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 16374
UFG | 2 | 3200 | 0 | 5 | 5 | 2145 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 12845
USAC | 3 | 4800 | 0 | 6 | 6 | 2574 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 16374
UNAH | 3 | 5360 | 0 | 5 | 5 | 2145 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 15005
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
 |  |  |  |  |  |  | repository. 80-100pg Language: English
D3.2 | Report on workshops and training sessions on digital skills | 3 | UCV | R | SEN | M32 | Conduct workshops and training sessions on digital skills (e.g., AI, data analysis, big data management) tailored to the needs of physics and related disciplines .
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 10
Work Package 4: Quality Plan, |  |  |  |  |  |  |  |  |  |  |  | 
Duration: |  | M | 3 - M | 36 |  | Lead Beneficiary: Universidad Industrial de Santander and Universidad de El Salvador |  |  | UIS (Coord) and UES (Deputy) |  |  | 
Objectives |  |  |  |  |  |  |  |  |  |  |  | 
Develop the Quality Assurance Plan for the project, the Code of Conduct, the Gender Policy, and Data Management Plan. Develop regular evaluations to follow up on the evolution of the different WP task and feedback mechanisms, |  |  |  |  |  |  |  |  |  |  |  | 
Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  | 
Task No | Nombre |  |  |  |  |  | Descripción |  |  | Participantes |  | Status
T4.1 | Quality Assurance Plan for the project |  |  |  |  |  | Develop and implement a General Quality Assurance Plan that outlines the procedures and standards to ensure the quality of the project. |  |  | UPCité, UAN and UES |  | Diciembre 2024 a febrero de 2025 Socializarlo con todos para recibir comentarios
T4.2 | Code of Conduct and a Gender Policy |  |  |  |  |  | Formulate a Code of Conduct and a Gender Policy to guide the behaviour and promote inclusivity within the project. |  |  | UT3, and USB |  | Marzo a agosto de 2025
T4.3 | Data Management Plan |  |  |  |  |  | Create a Data Management Plan to outline how data will be handled, stored and shared throughout the project. |  |  | INSA, and UFG |  | Marzo a agosto de 2025 Revisar si está publicado en la página de LA-CONGA, o pedirlo a JAL
T4.4 | Student's online questionnaires |  |  |  |  |  | Design and implement online questionnaires to collect feedback from current and former students about the quality of their training. |  |  | USal, UCV and UNAH |  | 2026 -2
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
UNMSM | 3 | 4800 | 0 | 5 | 5 | 2145 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 14445
UCV | 5 | 8560 | 0 | 5 | 5 | 2145 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 18205
USB | 3 | 4800 | 0 | 4 | 4 | 1716 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 12516
Total | 53 | 120840 | 0 | 60 | 60 | 25740 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 236580
Work Package 4
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 11
T4.5 | Encuestas al staff |  |  | Diseñar y llevar a cabo encuestas al personal para evaluar los recursos e instalaciones de enseñanza |  |  | USAC, UNMSM and UIS BEN |  |  |  | 2026 -2 |  | 
T4.6 | Communication Effectiveness |  |  | Después de la publicación, monitorear las interacciones en redes sociales y sitios web (del proyecto, las comunidades y la Pasarela Científica) para medir la efectividad de los mensajes, realizando ajustes o generando nuevos mensajes según sea necesario para optimizar la estrategia de comunicación.. |  |  | UIS, UNAB, UES, UT3, UAN BEN |  |  |  | Marzo 2025 a noviembre de 2027 |  | 
Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  | 
Milestone No (continuous numbering not linked to WP) |  | Milestone Name | Work Package No |  | Lead Beneficiary | Description |  |  | Due Date (month number) |  |  |  | Means of Verification
MS4.1 |  | First year of survey for staff and students | 4 |  | UIS and UES | Implement and evaluate the surveys for staff and students about the quality of the training (courses and internships) the conduct of the staff and the teaching resources and facilities |  |  | 24 |  |  |  | The results of the surveys and their evaluation
MS4.2 |  | Second year of survey for staff and students | 4 |  | UIS and UES | Implement and evaluate the surveys for staff and students about the quality of the training (courses and internships), the conduct of the staff and the teaching resources and facilities |  |  | 36 |  |  |  | The results of the surveys and their evaluation
Deliverable No (continuous numbering linked to WP) |  | Deliverable Name | Work Package No |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) | 
D4.1 |  | MidTerm Report | 4 and 6 |  | UAN, UPCité, UIS and UES | R |  | SEN |  | 23 |  | An exhaustive report concluding the first year of courses, aimed at assessing the overall quality of the project and identifying improvement for the upcoming year. Format: electronic doc in a repository. 80-100pg Language: English | 
D4.2 |  | First cohort of survey for staff and students | 4 |  | USAC | R |  | SEN |  | 25 |  | Report on the results of the survey of first-cohort | 
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 12
WP4 Estimated budget — Resources (n/a for prefixed Lump Sum Grants) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Participant | Costs |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A. Personnel [Pers/month ¦Eur] |  | B. Subcontrac t | C.1a Travel |  |  | C.1b Accomod | C.1c Subsist | C.2 Equipment | C.3 Goods and services | D.1 Support to third parties |  | E. Indirect costs | Total costs
UPCité | 1 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600
UT3 | 1 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600
INSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
USal | 1 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600
UIS | 1 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160
UAN | 3 | 6480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6480
UNAB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
USFQ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ESPOC H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
USAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNAH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNMSM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UCV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
USB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 7 | 25440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25440
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
 |  |  |  |  |  |  | including staff and students.
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 13
Work Package 5: Dissemination, Awareness, and Exploitation. |  |  |  |  |  |  |  |  |  |  |  | 
Duration: |  | M | 1 - M | 36 |  | Lead Beneficiary: Universidad Autónoma de Bucaramanga and Universidad Francisco Gavidia |  |  | UNAB (Coord) and UFG (Deputy) |  |  | 
Objectives |  |  |  |  |  |  |  |  |  |  |  | 
Enhancing Project Visibility and Outreach Promoting Knowledge Dissemination and Engagement Boosting the Importance of Open Science and Digital Education |  |  |  |  |  |  |  |  |  |  |  | 
Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  | 
Task No | Nombre |  |  |  |  |  | Descripción |  |  | Participantes |  | Status
T5.1 | Communication Plan |  |  |  |  |  | Desarrollo e implementación del Plan de Comunicación. Definir la identidad visual del proyecto, las líneas temáticas para una construcción coherente del discurso, los roles de los portavoces y los mecanismos para compartir información oportuna sobre el proyecto y el progreso de la comunidad. |  |  | UNAB, UIS, UFG |  | Diciembre 2024 a febrero de 2025
T5.2 | Website and social network profile |  |  |  |  |  | Desarrollar el sitio web y el perfil en redes sociales del proyecto y de las cuatro comunidades de investigación. |  |  | UNAB, and UIS |  | Diciembre 2024 a febrero de 2025
T5.3 | Periodic information feeds in social networks and the website |  |  |  |  |  | Campaña periódica en diferentes medios de comunicación publicando el avance del proyecto, las actividades de la comunidad y del proyecto (seminarios, reuniones y talleres, hackatones); la apertura de nuevas cohortes de cursos; las escuelas de la red. |  |  | UNAB and UCV |  | Marzo de 2025 a noviembre de 2027
T5.4 | Communication support for other WPs |  |  |  |  |  | Apoyo y revisión de textos para otros Paquetes de Trabajo (WP) en el desarrollo de piezas de información, informes y comunicaciones para conferencias, y artículos de revistas. Desarrollar y mantener el sitio web de la Pasarela Científica (Science Gateway). |  |  | UNAB, UNMSM, UIS, BEN |  | Diciembre de 2024 a noviembre de 2027
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
Work Package 5
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 14
Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  | 
Milestone No | Milestone Name | Work Package | Lead Beneficiary | Description |  | Due Date |  |  | Means of Verification
MS5.1 | Project Website and social network profile | 5 | UNAB | Launch of the project website and first post in social networks |  | M3 |  |  | Access to the project website and social network
MS5.2 | Community Websites and social network profiles | 5 | UNAB | Launch of the website for each community |  | M6 |  |  | Access to the community websites and social network
MS5.3 | 500 post landmark | 5 | UNAB | Reach the 500 post in all the network profile |  | M20 |  |  | Access to the community social network profiles
Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type | Dissemination Level |  | Due Date (month number) | Description (including format and language) | 
D5.1 | Communication Plan | 5 | UNAB | R | SEN |  | M3 | Develop a Communication Plan outlining strategies for sharing project information, including visual identity, thematic discourse, spokesperson roles, and progress mechanisms. Communicate objectives, achievements, and social impact to diverse audiences. Format: electronic doc in a repository. 80-100pg Language: English | 
WP5 Estimated budget — Resources (n/a for prefixed Lump Sum Grants) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Participant | Costs |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A. Personnel [Pers/month ¦Eur] |  | B. Subcontrac t | C.1a Travel |  |  | C.1b Accomod | C.1c Subsist | C.2 Equipment | C.3 Goods and services | D.1 Support to third parties |  | E. Indirect costs | Total costs
UPCité | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 15
Work Package 6: Management |  |  |  |  |  |  |  | 
Duration: | M | 1 - M | 36 |  | Lead Beneficiary: Universidad Antonio Nariño and Université Paris Cité |  | UAN (coord) and UPCite (Deputy) | 
Objectives |  |  |  |  |  |  |  | 
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
UT3 INSA USal UIS UAN UNAB USFQ EsPoCh UES UFG USAC UMG UNAH UNI UNMSM UCV USB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 1 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160
 | 5 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800
 | 4 | 7520 | 16956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24476.0
 | 1 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 11 | 22640 | 16956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39596
Work Package 6
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 16
Implementar mecanismos de comunicación robustos y fáciles de usar para simplificar la interacción fluida entre los socios del consorcio. Establecer y mantener cronogramas detallados del proyecto para asegurar la finalización oportuna de cada fase y de los objetivos del proyecto. Proporcionar pautas integrales para la presentación de informes internos y externos de manera coherente y precisa, asegurando que todos los representantes institucionales estén informados sobre el progreso y los desafíos. Monitorear y gestionar el presupuesto del proyecto para asegurar que todas las actividades sean rentables y que los recursos financieros se empleen de manera óptima. |  |  |  |  |  |  |  |  |  | 
Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  | 
Task No | Nombre |  |  | Descripción |  |  | Participantes |  | Status | 
T6.1 | EL-BONGO physics Kick-off meeting |  |  | Esta reunión inicial reúne a todos los miembros institucionales, permitiendo una comprensión compartida de los objetivos, cronogramas, roles y responsabilidades del proyecto. Es una oportunidad para fomentar la cohesión del equipo y alinear las expectativas de todos. |  |  | UAN, UPCité and UIS |  | Diciembre de 2024 a febrero de 2025 OK | 
T6.2 | WP leader meeting |  |  | Reunión semanal corta con los líderes de WP para dar seguimiento a la ejecución del proyecto. |  |  | UAN, UPCité, UNMSM, USal, UIS, and UNAB |  | Diciembre 2024 a noviembre de 2027 | 
T6.3 | Executive Board Meetings |  |  | Reunión mensual con los líderes de WP y los representantes institucionales para informar sobre los avances y los problemas de ejecución. |  |  | UAN and All the consortium institutions |  | Diciembre 2024 a noviembre de 2027 | 
T6.4 | External Advisory Meetings |  |  | Reunión anual con el Consejo Asesor Externo. |  |  | UAN, UPCité and UIS |  | Septiembre a noviembre de 2025 – OK, 2026, 2027 | 
T6.5 | Midterm meeting and report |  |  | Reunión de mitad de periodo para evaluar los avances del proyecto y los cambios estratégicos necesarios para lograr todos los objetivos del proyecto. |  |  | UPCité All the consortium institutions |  | Marzo a mayo de 2026 Apenas terminen los primeros módulos en marzo 2026, hacer un reporte sobre eso. | 
Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  | 
Milestone No |  | Milestone Name | Work Package |  | Lead Beneficiary | Description |  | Due Date |  | Means of Verification
MS6.1 |  | First EAB meeting | 6 |  | UAN, UPCite | It provides an unbiased perspective on the project's progress, helping identify strengths and improvement areas. |  | M12 |  | Meeting Minutes
MS6.2 |  | Midterm meeting | 6 |  | UAN, UPCite | Midterm meeting to evaluate the advances of the project and the strategic changes needed to accomplish all project goals |  | M18 |  | Meeting Minutes
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 17
MS6.3 | Second EAB meeting | 6 | UAN, UPCite | It provides an unbiased perspective on the project's progress, helping identify strengths and improvement areas. |  | M24 |  |  | Meeting Minutes
MS6.4 | Third EAB meeting | 6 | UAN, UPCite | It provides an unbiased perspective on the project's progress, helping identify strengths and improvement areas. |  | M35 |  |  | Meeting Minutes
Deliverable No | Deliverable Name | Work Package | Lead Beneficiary | Type | Dissemination Level |  | Due Date | Description | 
D6.1 | Quality assurance mid-term Report (Management) | 6 | UAN | R | SEN |  | M18 | The midterm report is crucial for assessing progress, identifying challenges, ensuring efficient resource utilisation, and making necessary adjustments to stay on track towards achieving project goals. Format: electronic doc in a repository. 80-100pg Language: English | 
WP6 Estimated budget — Resources (n/a for prefixed Lump Sum Grants) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Participan t | Costs |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A. Personnel [Pers/month ¦Eur] |  | B. Subcontrac | C.1a Travel |  |  | C.1b Accomod | C.1c Subsisten | C.2 Equipment | C.3 Goods and services | D.1 Support to third parties |  | E. Indirect costs | Total costs
UPCité | 1 | 5600 | 0 | 4 | 4 | 5504 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 13184
UT3 | 0 | 0 | 0 | 4 | 4 | 5504 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 7584
INSA | 0 | 0 | 0 | 4 | 4 | 5504 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 7584
USal | 0 | 0 | 0 | 4 | 4 | 5504 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 7584
UIS | 1 | 2160 | 0 | 6 | 6 | 2574 | 1560 | 1560 | 0 | 0 | 0 | 0 | 0 | 7854
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 18
UAN | 8 | 17280 | 0 | 6 | 6 | 2574 | 1560 | 1560 | 0 | 0 | 0 | 0 | 0 | 22974
UNAB | 0 | 0 | 0 | 2 | 2 | 858 | 520 | 520 | 0 | 0 | 0 | 0 | 0 | 1898
USFQ | 0 | 0 | 0 | 4 | 4 | 1716 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 3796
EsPoCh | 0 | 0 | 0 | 2 | 2 | 858 | 520 | 520 | 0 | 0 | 0 | 0 | 0 | 1898
UES | 0 | 0 | 0 | 3 | 3 | 1287 | 780 | 780 | 0 | 0 | 0 | 0 | 0 | 2847
UFG | 0 | 0 | 0 | 3 | 3 | 1287 | 780 | 780 | 0 | 0 | 0 | 0 | 0 | 2847
USAC | 0 | 0 | 0 | 3 | 3 | 1287 | 780 | 780 | 0 | 0 | 0 | 0 | 0 | 2847
UMG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNAH | 0 | 0 | 0 | 3 | 3 | 1287 | 780 | 780 | 0 | 0 | 0 | 0 | 0 | 2847
UNI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNMSM | 0 | 0 | 0 | 6 | 6 | 2574 | 1560 | 1560 | 0 | 0 | 0 | 0 | 0 | 5694
UCV | 1 | 2160 | 0 | 4 | 4 | 1716 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 5956
USB | 0 | 0 | 0 | 4 | 4 | 1716 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 3796
Total | 11 | 27200 | 0 | 62 | 62 | 41750 | 16120 | 16120 | 0 | 0 | 0 | 0 | 0 | 101190
Staff effort per work package Fill in the summary on work package information and effort per work package. |  |  |  |  |  | 
Work Package No | Work Package Title | Lead Participant No | Lead Participant Short Name | Start Month | End Month | Person-Months
1 | Preparation | 4 | USal | 1 | 7 | 5
2 | Developing and Tools | 16 | UNMSM | 5 | 24 | 21
3 | Training and Education | 17 | UCV | 13 | 36 | 53
4 | Quality Plans | 5 | UIS | 3 | 36 | 7
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
Staff effort (n/a for Lump Sum Grants)
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024

## Slide 19
5 | Dissemination, Awareness, and Exploitation | 7 | UNAB | 1 | 36 | 12
6 | Management | 6 | UAN | 1 | 36 | 23
 |  |  |  |  | Total Person- Months | 121
Staff effort per participant Fill in the effort per work package and Beneficiary/Affiliated Entity. Please indicate the number of person/months over the whole duration of the planned work. Identify the work-package leader for each work package by showing the relevant person/month figure in bold. |  |  |  |  |  |  | 
Participant | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | Total Person-Months
UPCité | 0 | 1 | 4 | 1 | 0 | 1 | 7
UT3 | 0 | 0 | 2 | 1 | 0 | 1 | 4
INSA Lyon | 0 | 0 | 2 | 0 | 0 | 1 | 3
USal | 1 | 0 | 3 | 1 | 0 | 1 | 6
UIS | 1 | 3 | 4 | 1 | 1 | 1 | 11
UAN | 2 | 6 | 7 | 3 | 5 | 8 | 31
UNAB | 0 | 1 | 3 | 0 | 4 | 1 | 9
USFQ | 0 | 1 | 3 | 0 | 1 |  | 6
EsPoCh | 0 | 1 | 3 | 0 | 0 | 1 | 5
UES | 0 | 1 | 3 | 0 | 0 | 1 | 5
UFG | 0 | 1 | 2 | 0 | 0 | 1 | 4
USAC | 1 | 1 | 3 | 0 | 0 | 1 | 6
UNAH | 0 | 1 | 3 | 0 | 0 | 1 | 5
UNMSM | 0 | 2 | 3 | 0 | 0 | 1 | 6
UCV | 0 | 1 | 5 | 0 | 0 | 1 | 7
Call: ERASMUS-EDU-2024-CBHE-STRAND-2 — [insert call name]
EU Grants: Application form (ERASMUS BB and LS Type II): V2.0 – 01.06.2022
Associated with document Ref. Ares(2024)8163905 - 18/11/2024